## Start Here
WIP Schedule for Concrete Contractors
Free template from ConstructiveCore. Your numbers stay in this file. It doesn't connect to anything.
What a WIP schedule tells you
The question it answers | For every open job: have you billed more or less than the work you've actually done? And is the job still on track to make the margin you bid?
Why your surety and bank care | Bonding companies and lenders use WIP to judge whether your reported profit is real. Big underbillings look like hidden losses. Big overbillings are cash you owe back in future work.
Underbilled | You've done more work than you've billed. It's money you've earned but not collected, or a sign the job is running over on cost.
Overbilled | You've billed ahead of the work. Good for cash now, but it's a liability: you still owe that work.
Start small: your 3 biggest jobs, ballpark numbers (5 minutes)
1. Go to the WIP Schedule tab | Type over the grey EXAMPLE row. Start with your 3 biggest open jobs. Round numbers from memory are fine.
2. The quick version | For each job you only need three things: contract amount, billed to date, and your gut feel for % complete. That's enough to see whether you're over- or underbilled.
3. The accurate version | Add estimated total cost and cost to date when you have them. The sheet then uses cost to measure % complete (what your surety expects) and flags jobs whose cost has passed the estimate.
4. Check the Summary tab | Your net over/under billing, the most underbilled jobs, and charts of where the money stands.
Heads up: cost to date is the hard part
Why it's hard | QuickBooks can report cost by job, but only if every bill, card charge and payroll hour was tagged to the job when it was entered. In most contractors' books, a lot of it isn't, so costs pile up with no job attached.
Quick check | Run Job Profitability Summary (QuickBooks Desktop) or Profit and Loss by Customer (QuickBooks Online). Compare its total cost to the total cost on your P&L. The gap is cost that isn't on any job, and every job looks more profitable than it really is.
If you get stuck here | That's normal, and it's the most useful thing this sheet can show you. Use your gut % complete for now. Getting job costs right without the hunting is exactly what ConstructiveCore does: every bill is tied to its job through the PO, automatically.
Settings
Flag a job when over/under billing exceeds | 5%
Percent of contract amount. 5% is a common starting point; change it if you like.
Definitions
Contract amount | Original contract plus approved change orders. Leave out pending change orders.
Estimated total cost | What you expect the job to cost when it's done: your bid cost, updated if you know it has changed.
% complete | If you entered estimated cost and cost to date: cost to date ÷ estimated total cost (the cost-to-cost method most sureties expect). Otherwise, your own % complete. Capped at 100%. The Method column shows which one was used.
Earned revenue | % complete × contract amount: what you've earned so far.
Over/(under) billed | Billed to date − earned revenue. Positive = overbilled, negative = underbilled.
Projected gross profit | Contract amount − estimated total cost.
Want this every week without the typing?
ConstructiveCore | ConstructiveCore keeps WIP, job costs, POs and billing up to date for every job, in sync with QuickBooks. See it at constructivecore.app
Note on C25: Percent of contract amount. 5% is a common starting point; change it to suit your business.

## WIP Schedule
WIP Schedule
Quick version: contract, billed to date and your % complete. Grey cells calculate on their own. |  |  | As of:
Job name | Customer / GC | Contract amount (incl. approved COs) | Estimated total cost (optional) | Cost to date (optional) | Billed to date | Your % complete (if no cost data) | Projected gross profit | Projected GP % | % complete | Method | Earned revenue | Over/(under) billed | Cost to complete | Left to bill | Status | _rank | _rank2 | _abs
EXAMPLE: Riverside warehouse slab (type over me) | Example GC | 480000 |  |  | 240000 | 60%
Totals
Note on E2: Date your costs and billings are current through, e.g. month-end.
Note on A5: Example of the quick version: contract, billed to date and a gut-feel % complete. Type over this row.
Note on G5: Your best guess of how far along the job is. Only used when estimated cost or cost to date is blank.

## Summary
WIP Summary
As of
Open jobs
Total contract value
Estimated total cost
Projected gross profit
Projected GP % (jobs with est. cost)
Cost to date
Earned revenue
Billed to date
Total underbilled (asset)
Total overbilled (liability)
Net over/(under) billed
Backlog: revenue left to earn
Jobs flagged underbilled
Jobs flagged overbilled
Jobs over estimate (margin fade)
Most underbilled jobs
Job | Underbilled by | Status
Want this every week without the typing? ConstructiveCore keeps WIP up to date, in sync with QuickBooks: constructivecore.app
How to read the charts
Gold bars = underbilled: work done but not billed yet. Bill it.
Blue bars = overbilled: billed ahead of the work. You still owe that work.
Red status on the WIP Schedule tab = over estimate: cost is already past the estimate, so margin is fading.
Charts

## Chart Data (hidden)
Helper data for the Summary charts. Calculated automatically; no need to edit.
Job | Underbilled | Overbilled | Value | Status | Jobs | Measure | Amount
|  |  |  | On track |  | Contract value
|  |  |  | Underbilled |  | Earned revenue
|  |  |  | Overbilled |  | Billed to date
|  |  |  | Over estimate |  | Cost to date